## Applicant Summary
APPLICANT SUMMARY
For the following six rows, enter info requested in the cell to the right, in column B.
Lead Applicant: | Newberry Springs Community Service District
Proposal Name: | Newberry Springs Community Enhancement Project
Jurisdiction: | Unincorporated San Bernardino County
Main Contact: | Rose Beardshear
Email: | rosebeardshear@gmail.com
Phone: | 760-447-6295
Instructions: Add more rows for additional co-applicants as needed.
Applicant Type | Name | Entity Type | If "Other", please describe | Email | Mailing Address
Lead Applicant | Newberry Springs Community Service District | Local Government |  | rosebeardshear@gmail.com | 30884 Newberry Road, Newberry Springs CA 92365
Co-Applicant | Main Street Murals | Nonprofit Organization |  | jane@desertdiscoverycenter.com | PO Box 1117, Barstow, CA 92312
Co-Applicant
Co-Applicant
Co-Applicant
Co-Applicant
Co-Applicant
Co-Applicant
Co-Applicant
Co-Applicant
Co-Applicant
Co-Applicant
Co-Applicant
Co-Applicant
Co-Applicant

## Newberry Work Plan
WORK PLAN
For the following three rows, information will automatically populate in the associated cell to the right, in column B.
Lead Applicant: | Newberry Springs Community Service District
Proposal Name: | Newberry Springs Community Enhancement Project
Jurisdiction: | Unincorporated San Bernardino County
Instructions: List primary responsible parties only. Represent timeline in months, e.g. Month 1 - Month 6.
Project Description: (500 character limit) | The Newberry CSD will lead planning efforts and program development for upgrades to an existing community center and parkland, a new civic hub, and a new electric transit service. Plans are focused around sustainability, climate solutions, improving public health and workforce development. Main Street Murals will partner with CSD for design elements and concepts. The work plan sets the foundation for social and economic vitality in this sensitive Mojave environment along historic Route 66.
Character Count | 500
TASK 1: Program Initiation
Subtask | Description | Deliverables/Milestones | Responsible Parties | Timeline
A. Stakeholder Kick-off. | Team meeting to initiate efforts and to establish project expectations. | 1. Meeting Materials. 2. Outcomes Summary. | CSD, Main Street Murals | Month 1-2
Outline a Community Engagement Strategy and develop project management framework. | Develop strategy and framework that to review, communications, schedule, and resource planning. | 1. Engagement Strategy. 2. Project Management Framework Memorandum. | CSD | Month 1 -2
B Grant Administration. | Provide monthly invoicing and status reports to Grantors | 1. Monthly Invoicing 2. Status Reports | CSD, Main Street Murals | Month 1-6
C. Consultant Selection Process. | Select Consultants through letter RFP process. | Consultant Solicitation & Award | CSD | Month 1-24
TASK 2: Community Center and Parkland Planning, Design, and Engagement
Subtask | Description | Deliverables/Milestones | Responsible Parties | Timeline
A: Community Center Upgrade | Conduct a feasibility analysis for Community Center preservation and upgrades. Entails evaluation of structural, electrical, water, and amenities, including health and safety elements. The Center serves as the facility for many of the programs outlined in this workplan. As a result, feasibility has been included in the planning phase. | 1. Structural/Seismic Report. 2. Mechanical/Electrical/Plumbing Evaluation. 3. Real Estate Condition Evaluation. 4. Feasibility Memorandum for Upgrade of Use including Emergency Center and Kitchen Center for Cottage Industry and Senior Meal Program. | CSD | Month 3-14.
B: Park Improvements | Evaluate park upgrade needs including electrical, landscaping, parking, recreational facilities, restrooms, and interpretive ADA trail to serve community and promote tourism. | Park Improvement Concept Plan. | CSD, Main Street Murals | Month 3-14.
C. Community Kitchen Upgrade | Develop a community based kitchen design concept and program proposal for operating the community-based kitchen which will include senior meals, workforce training and social enterprise opportunities to support food resilience and economic development for the community. | 1. Kitchen design concept 2. Detailed Program Strategy | CSD, Supporting Partners | Month 3-12
D. Transit Service Plan | Evaluate options for a new electric transit service that connects residents and visitors to CSD programs and activities. | Transit Service Plan. | CSD | Month 10-16
E. Community Outreach. | Conduct three (3) community outreach meetings to solicit input for all tasks. Meetings to share findings to-date and solicit input for proposed Community Center, park, community kitchen, and transit service updgrades. | 1. Meeting Materials. 2. Advertising Collateral. 3. Outcomes Summary. | CSD, Main Street Murals | Month 4, Month 10, Month 16
TASK 3: Civic Hub Planning
Subtask | Description |  | Responsible Parties | Timeline
A. Further Civic Hub Planning. | Further engagement and feasibility studies on a proposed centralized Civic Hub to improve the delivery of authorized CSD services and other services desired and needed by the community. | Civic Hub Strategies Memorandum. | CSD | Month 10-20
B. Community Outreach. | Conduct One (1) community outreach meeting to solicit input on Civic Hub ideas. Meeting to share findings to-date and solicit input for proposed Civic Hub and associated community activities activities or programs. | 1. Meeting Materials . 2. Advertising Collateral. 3. Outcomes Summary. | CSD | Month 15
Task 4: Program Implementation Plan
Subtask | Description | Deliverables/Milestones | Responsible Parties | Timeline
A. Budgets. | Develop budgets for program elements. | Program Implementation Plan. | CSD | Month 18-22
B. Funding and Financing Opportunities. | Identify program funding and financing partners and initiate discussions. | Program Implementation Plan. | CSD | Month 18-22
C. Schedule. | Delineate potential program schedule. | Program Implementation Plan. | CSD | Month 18-22
D. Partnerships. | Establish and identify program partners and initiate discussions. | Program Implementation Plan. | CSD | Month 18-22
E. Climate & Equity Metrics. | Assess GHG Impacts, equity, resilience, and sustainability aspects of the program. | Program Implementation Plan. | CSD | Month 18-22
F. Development Needs. | Identify design, permittting, property, and CEQA requirements. | Program Implementation Plan. | CSD | Month 18-22
G. Community Outreach. | Conduct One (1) community outreach meeting to solicit input on final recommendations. | 1. Meeting Materials 2. Advertising Collateral 3. Outcomes Summary | CSD | Month 20

## Newberry Budget
BUDGET
For the following three rows, information will automatically populate in the associated cell to the right, in column B.
Lead Applicant: | Newberry Springs Community Service District
Proposal Name: | Newberry Springs Community Enhancement Project
Jurisdiction: | Unincorporated San Bernardino County
Cap/Threshold Summary Table | Direct Costs | Indirect
Cap/Threshold | 88-100% | 12%
Calculated | 88.27% | 11.73%
Total | 263500 | 35000
Cost Description | Cost Type | Cost per unit | Number of Units | Total TCC Grant Funds | Task 1 | Task 2 | Task 3 | Task 4 | Check (Sum of Tasks = Total TCC Grant Funds)
Main Street Murals Artist | Co-Applicants/Partners Personnel | 14700 | 1 | 14700 | 1000 | 11700 | 0 | 2000 | TRUE
CSD General Manager | Grantee Personnel | 25200 | 1 | 25200 | 6300 | 8820 | 3780 | 6300 | TRUE | 25200
CSD Office Assistant | Grantee Personnel | 13200 | 1 | 13200 | 3300 | 4620 | 1980 | 3300 | TRUE
CSD Treasurer | Grantee Personnel | 7500 | 1 | 7500 | 1875 | 2625 | 1125 | 1875 | TRUE
Project Manager/Urban Designer | Grantee Personnel | 93600 | 1 | 93600 | 14040 | 46800 | 14040 | 18720 | TRUE
Grant Writer/Planner | Grantee Personnel | 69500 | 1 | 69500 | 10425 | 34750 | 10425 | 13900 | TRUE
Energy Consultant | Subcontractors | 5000 | 1 | 5000 | 0 | 5000 | 0 | 0 | TRUE
Facilities Inspector Consultant | Subcontractors | 5000 | 1 | 5000 | 0 | 5000 | 0 | 0 | TRUE
Food Services/Kitchen Consultant | Subcontractors | 3500 | 1 | 3500 | 0 | 3500 | 0 | 0 | TRUE
Structural Engineering Consultant | Subcontractors | 7500 | 1 | 7500 | 0 | 7500 | 0 | 0 | TRUE
Travel/Mileage | Travel | 7900 | 1 | 7900
Advertising/Media | Other Direct Costs | 2500 | 1 | 2500
Public Meeting Materials | Other Direct Costs | 2500 | 1 | 2500
Equipment | Other Direct Costs | 4100 | 1 | 4100
Printing & Mailing (including reports) | Other Direct Costs | 1800 | 1 | 1800
Indirect | Indirect Costs | 35000 | 1 | 35000 | 5250 | 17500 | 5250 | 7000 | TRUE
Totals |  |  |  | 298500 | 42190 | 147815 | 36600 | 53095 | #REF!

## Reference
Data Validation Tables - Do not edit.
Eligible Applicants
Community-based organization
Local government
Nonprofit Organization
Philanthropic organization or foundation
Faith-based organization
Coalition or association of nonprofit organizations
Community development financial institution
Community development corporation
Joint Powers Authority
Council of Governments
California Native American Tribe
Other
Cost Type
Grantee Personnel
Co-Applicants/Partners Personnel
Subcontractors
Supplies
Travel
Other Direct Costs
Indirect Costs